## Slide 1
Project Manager: Tricia Tan
Tsang Bao Xian | Casper Lim Zhi Xin | Ong Yan Ning | Loh Xiao Binn
Application Demo& Progress Update
IS212 Software Project Management
G4T4

## Slide 2
Functionalities
Wiki Question | Answer
Do you plan to drop/add any functionalities? | No
Do you plan to use any PHP frameworks? | No
Did you manage to finish login + 1 functionality? | Yes
What functionalities have you finished? | Login, add bid, bootstrap, [NEW] Update bid, delete bid, JSON web service (partial), round 1 clearing logic (partial)
What is the IP address & admin password for your cloud deployment? | IP Address: 54.169.210.219 Admin password: @dm1in5PM

## Slide 3
Schedule Overview
Weekly Meetings on Tuesdays and Fridays.
Task set on Friday has deadline on Tuesday  4 Working Days
Task set on Tuesday has deadline on Friday  3 Working Days

## Slide 4
Planned Iterations
Iteration | Task | Start Date | End Date
1 | Login, Add bid, Bootstrap Functionality | Monday of Week 5 | Sunday of Week 6
2 | Drop bid, Slides for PM review, Web service, Update bid | Monday of Week 7 | Thursday of Week 9
3 | Rounds, Drop section, Dumping | Friday of Week 9 | Thursday of Week 11
4 | Deploying to AWS, UAT, Check UAT results, testing, debugging, redeploy | Friday of Week 11 | Thursday of Week 13
5 | Prepare Final presentation slides | Friday of Week 13 | Sunday of Week 14
Status: On schedule

## Slide 5
Roles & Task Allocation
Tricia Tan
Project Manger, Coder
Loh Xiao Binn
Coder
d
Bao Xian
Coder
Yan Ning
Coder
Casper Lim
Coder

## Slide 6
Milestones and PMs in-charge
27 Sep
3 Oct
17 Oct
17 Oct
31 Oct
31 Oct
14 Nov
17 Nov
21 Nov
End of Iteration 1
PM: Bao Xian
End of Iteration 2
PM: Tricia
End of Iteration 3
PM: Xiao Binn
End of Iteration 4
PM: Casper
Final Presentation
PM: Yan Ning
PM Review
PM: Bao Xian
Application Demo
PM: Tricia
User Acceptance Test (UAT)
PM:Xiao Binn
Final Submission
PM: Casper

## Slide 7
Buffer Time
Deadlines set at next meeting
Taking over/ Helping each other at meetings if any of us face any difficulties
Use Meeting time as buffer to debug

## Slide 8
Critical Paths
(Iteration 2)
Number of critical paths: 2

## Slide 9
Add bid validation
1
1
2
2
2
Update bid
3
4
5
5
3
Testing & Debugging
6
6
6
6
1
Round 1 logic
7
7
8
8
2
Testing & Debugging
9
9
9
9
1
JSON checker
3
3
3
3
1
Update bid (JSON)
4
5
5
6
2
Delete bid (JSON)
6
7
7
8
2
Authentication
4
4
4
4
1
Testing & Debugging
5
5
5
5
1
Bootstrap
6
6
8
8
3
Create dump table
4
7
4
7
1
Create dump (user)
5
8
5
8
1
Testing & Debugging
9
9
9
9
1
Integration
10
10
10
10
1
Testing & debugging
11
11
11
11
1
Deployment
12
12
12
12
1
PM review slides
11
13
12
13
2
Working prototype
13
13
13
13
1
App demo, update process
14
14
14
14
2
Iteration 2
End
1
3
3
1
1

## Slide 10
Bug Metrics
(Iteration 2)
Current Bug Metrics:
Did you have to take any action according to your mitigation plan?
Debugging sessions are arranged when iteration points > 10
Debugging session was carried out during group meetings
0

## Slide 11
Paired Programming Rotation
(Iteration 2)
Update Bid
function
Yan Ning,
Tricia
Drop/Delete Bid
function
Casper,
Xiao Binn
JSON
Web Service
Casper,
Bao Xian
Round 1 Clearing Logic
Xiao Binn,
Tricia

## Slide 12
Thank You