## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (User) | No error message displayed during authenication | High | 5 | 0 | Use the planned debugging time in the iteration.
2 | 1 | Bootstrap | Crashes on upload with a "duplicate entry" database error - foreign key error | High | 5
3 | 1 | Bootstrap | Issues with sort.php (line 11) after adding bootstrap validations | High | 5
4 | 1 | Bootstrap | Syntax error or access violation: unable to drop foreign key (Have to re-execute all of the sql statements) | High | 5
5 | 1 | Bootstrap | Bootstrap bid edollar validation will have error if the e-dollar have one decimal place | Critical | 10
6 | 1 | Bootstrap | Integrity constraint violation of duplicate entry when there are duplicated names | High | 5
7 | 1 | Bootstrap | Whitespacing characters in data not removed before storing into database | High | 5
8 | 1 | Bootstrap | Invalid course not validated and reported | High | 5
9 | 1 | Bootstrap | Error in If statement for 'Class clash' validation | High | 5
10 | 1 | Bootstrap | Error in If statement for 'Exam clash' validation | High | 5
11 | 1 | Bootstrap | Truncate table for student and course error | High | 5
12 | 1 | Bootstrap | Wrong format for eDollars | Low | 1
13 | 1 | Bootstrap | Exceed eDollar amount limit | High | 5
14 | 1 | Bootstrap | Wrong format for isCourseExist and isUseridExisit | Low | 1
15 | 1 | Bootstrap | Wrong output for RetrieveCourseCompleted function | High | 5
16 | 1 | Bootstrap | Total sum of edollar return null | High | 5
17 | 1 | Bootstrap | All validations across all objects to see if data exist in the database are not working | Critical | 10
18 | 1 | Bootstrap | Invaild user, course, prerequisite, section error | High | 5
19 | 1 | Add Bid | "Call to a member function getCourse()" error prompted upon clicking "place bids" button | High | 5
20 | 2 | Update Bid | Errors prompted when users did not update any bids upon clicking "update button" | High | 5 | 0
21 | 2 | Login (User) | Successful login does not redirect to welcome page | Critical | 10 |  | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
22 | 2 | Authenticate (web service) | Wrong username does not give expected output | Low | 1 | 0
23 | 2 | Bidding | Selecting 2 sections of the same course to cart only displays 1 of the sections in final cart | High | 5
24 | 2 | Bidding | Error message appears when bid with no amount stated | Low | 1
25 | 2 | Bidding | Inaccurate reflection when 2 or more of the same section is selected to cart | High | 5 |  | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
26 | 2 | Add Bid | Other course section (which users did not want to bid for) appeared upon placing bids for the selected course section that users want. | Low | 1 | 0
27 | 2 | Update Bid | Student can update bid with less than e$10 | High | 5
28 | 2 | Update Bid | Student can update bid with e$ of more than 2 decimal places | High | 5
29 | 2 | Delete Bid | Failed to delete bid. Successful deletion message shows even before user selects section to delete. | Critical | 10
31 | 2 | Add Bid | Small typo on error message - "Invalid Amount (more than 10 and les than 999)" | Low | 1
32 | 2 | Update Bid | Errors when updating bid - non numeric value encountered | High | 5
33 | 2 | Update Bid | Errors when updating bid - uncaught argument count error due to too few arguments to function BidDAO. | High | 5
34 | 2 | Bootstrap | Integrity constraint violation - cannot delete or update a parent row | High | 5
35 | 2 | Update Bid | Invalid amount even though the amount is valid | High | 5
36 | 3 | Rounds | Wrong output for stopping round 2 | Low | 1 | 0
37 | 3 | Update Bid | Update bid exceed limit even when it did not | High | 5
38 | 3 | Update Bid | Round 2 update bid status is affected by other bids if there is multiple update at once | High | 5
39 | 4 | Bootstrap | Timetable clashes when it is not suppose to clash | High | 5 | 0
40 | 4 | Bootstrap | Bootstrap edollar validation displayed insufficient edollar despite have enough money | High | 5
41 | 4 | Bootstrap | Minimum bid is wrong when the number of successful bid is equal to the number of vacancy | High | 5
42 | 4 | Add Bid | Errors prompted when users try to place bids in inactive round (when admin hasn't bootstrap to start the rounds) | High | 5
43 | 4 | Add Bid | Errors prompted in students interface after starting round 2 | High | 5
44 | 4 | Add Bid | Some of the user that have completed the prerequiste aren't allowed to bid for their elligble course. | High | 5
45 | 5 | Update/Delete Bid | Users are able to update and delete bid even though round has not begin yet | High | 5
46 | 5 | Drop section | Users are able to drop section even though round has not begin yet | High | 5
47 | 5 | Bootstrap | Uncaught error: Call to a member function getEdollar() upon importing bootstrap files with whitespacing characters at the start and end of certain fields | High | 5
48 | 5 | Bootstrap | Illegal string offset and invalid arguments error when admin click "import" button directly without importing any files | High | 5
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (User) | No error message displayed during authenication | Resolved | 2019-09-23 | 2019-09-23 | BX & Tricia
2 | 1 | Bootstrap | Crashes on upload with a "duplicate entry" database error - foreign key error | Resolved | 2019-09-23 | 2019-09-23 | BX & Tricia
3 | 1 | Bootstrap | Issues with sort.php (line 11) after adding bootstrap validations | Resolved | 25/09/2019 | 25/09/2019 | BX & Tricia
4 | 1 | Bootstrap | Syntax error or access violation: unable to drop foreign key (Have to re-execute all of the sql statements) | Resolved | 25/09/2019 | 26/09/2019 | BX
5 | 1 | Bootstrap | Bootstrap bid edollar validation will have error if the e-dollar have one decimal place | Resolved | 25/09/2019 | 26/09/2019 | BX
6 | 1 | Bootstrap | Integrity constraint violation of duplicate entry when there are duplicated names | Resolved | 25/09/2019 | 26/09/2019 | BX
7 | 1 | Bootstrap | Whitespacing characters in data not removed before storing into database | Resolved | 25/09/2019 | 26/09/2019 | BX
8 | 1 | Bootstrap | Invalid course not validated and reported | Resolved | 26/09/2019 | 26/09/2019 | BX
9 | 1 | Bootstrap | Error in If statement for 'Class clash' validation | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
10 | 1 | Bootstrap | Error in If statement for 'Exam clash' validation | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
11 | 1 | Bootstrap | Truncate table for student and course error | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
12 | 1 | Bootstrap | Wrong format for eDollars | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
13 | 1 | Bootstrap | Exceed eDollar amount limit | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
14 | 1 | Bootstrap | Wrong format for isCourseExist and isUseridExisit | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
11 | 1 | Bootstrap | Wrong output for RetrieveCourseCompleted function | Resolved | 2019-10-01 | 2019-10-01 | Casper & Tricia
12 | 1 | Bootstrap | Total sum of edollar return null | Resolved | 2019-10-02 | 2019-10-02 | Casper
17 | 1 | Bootstrap | All validations across all objects to see if data exist in the database are not working | Resolved | 2019-10-02 | 2019-10-02 | Casper
18 | 1 | Bootstrap | Invaild user, course, prerequisite, section error | Resolved | 2019-10-02 | 2019-10-02 | Casper
19 | 1 | Add Bid | "Call to a member function getCourse()" error prompted upon clicking "place bids" button | Resolved | 2019-10-02 | 2019-10-02 | Casper
20 | 2 | Update Bid | Errors prompted when users did not update any bids upon clicking "update button" | Resolved | 2019-10-07 | 2019-10-08 | Yan Ning
13 | 2 | Login (User) | Successful login does not redirect to welcome page | Resolved | 2019-10-10 | 2019-10-10 | Casper & Bao Xian
14 | 2 | Authenticate (web service) | Wrong username does not give expected output | Resolved | 2019-10-10 | 2019-10-11 | Casper & Bao Xian
23 | 2 | Bidding | Selecting 2 sections of the same course to cart only displays 1 of the sections in final cart | Resolved | 2019-10-11 | 16/10/2019 | Casper & Bao Xian
24 | 2 | Bidding | Error message appears when bid with no amount stated | Resolved | 2019-10-11 | 16/10/2019 | Casper
25 | 2 | Bidding | Inaccurate reflection when 2 or more of the same section is selected to cart | Resolved | 2019-10-11 | 16/10/2019 | Casper & Bao Xian
26 | 2 | Update Bid | Student can update bid with less than e$10 | Resolved | 15/10/2019 | 16/10/2019 | Casper
27 | 2 | Update Bid | Student can update bid with e$ of more than 2 decimal places | Resolved | 15/10/2019 | 16/10/2019 | Casper
28 | 2 | Delete Bid | Failed to delete bid. Successful deletion message shows even before user selects section to delete. | Resolved | 15/10/2019 | 15/10/2019 | Casper
29 | 2 | Add Bid | Small typo on error message - "Invalid Amount (more than 10 and les than 999)" | Resolved | 15/10/2019 | 15/10/2019 | Yan Ning
30 | 2 | Update Bid | Errors when updating bid - non numeric value encountered | Resolved | 15/10/2019 | 16/10/2019 | Casper
31 | 2 | Update Bid | Errors when updating bid - uncaught argument count error due to too few arguments to function BidDAO. | Resolved | 15/10/2019 | 16/10/2019 | Casper
32 | 2 | Bootstrap | Integrity constraint violation - cannot delete or update a parent row | Resolved | 2019-10-16 | 16/10/2019 | Casper & Bao Xian
33 | 2 | Update Bid | Invalid amount even though the amount is valid | Resolved | 2019-10-16 | 2019-11-05 | Casper & Tricia
34 | 2 | Bootstrap | Integrity constraint violation - cannot delete or update a parent row | Resolved | 2019-10-16 | 2019-11-05 | Casper & Tricia
35 | 2 | Update Bid | Invalid amount even though the amount is valid | Resolved | 2019-10-16 | 2019-11-05 | Casper & Tricia
36 | 3 | Rounds | Wrong output for stopping round 2 | Resolved | 21/10/2019 | 21/10/2019 | Bao Xian
37 | 3 | Update Bid | Update bid exceed limit even when it did not | Resolved | 24/10/2019 | 24/10/2019 | Casper
38 | 3 | Update Bid | Round 2 update bid status is affected by other bids if there is multiple update at once | Resolved | 24/10/2019 | 24/10/2019 | Casper
39 | 4 | Bootstrap | Exam and Class Timetable clashes when it is not suppose to clash | Resolved | 2019-11-05 | 2019-11-05 | Casper & Bao Xian
40 | 4 | Bootstrap | Bootstrap edollar validation displayed insufficient edollar despite having enough money | Resolved | 2019-11-05 | 2019-11-05 | Casper & Bao Xian
41 | 4 | Bootstrap | Minimum bid is wrong when the number of successful bid is equal to the number of vacancy | Resolved | 2019-11-05 | 2019-11-05 | Casper & Tricia
42 | 4 | Add Bid | Errors prompted when users try to place bids in inactive round (when admin hasn't bootstrap to start the rounds) | Resolved | 2019-11-07 | 2019-11-14 | Casper and Yan ning
43 | 4 | Add Bid | Errors prompted in students interface after starting round 2 | Resolved | 2019-11-14 | 2019-11-14 | Casper and Yan ning
44 | 4 | Add Bid | Some of the user that have completed the prerequiste aren't allowed to bid for their elligble course. | Resolved | 2019-11-14 | 2019-11-14 | Casper and Yan ning
45 | 5 | Update/Delete Bid | Users are able to update and delete bid even though round has not begin yet | Resolved | 2019-11-15 | 2019-11-15 | Casper and Yan ning
46 | 5 | Drop section | Users are able to drop section even though round has not begin yet | Resolved | 2019-11-16 | 2019-11-16 | Casper and Yan ning
47 | 5 | Bootstrap | Uncaught error: Call to a member function getEdollar() upon importing bootstrap files with whitespacing characters at the start and end of certain fields | Resolved | 2019-11-16 | 2019-11-16 | Casper and Yan ning
48 | 5 | Bootstrap | Illegal string offset and invalid arguments error when admin click "import" button directly without importing any files | Resolved | 2019-11-16 | 2019-11-16 | Casper and Yan ning