## Slide 1: SPM PM Review
G4T4
PM: Tsang Bao Xian
Casper Lim Zhi Xin, Tricia Tan Li Lin, Ong Yan Ning, Loh Xiao Binn

## Slide 2: Functionalities
Wiki Question | Answer
Do you plan to drop/add any functionalities? | No
Do you plan to use any PHP frameworks? | No
Did you manage to finish login + 1 functionality? | Yes
What functionalities have you finished? | Login, add bid, bootstrap
What is the IP address & admin password for your cloud deployment? | IP Address: 54.169.210.219 Admin password: @dm1in5PM

## Slide 3: Schedule Overview
Weekly Meetings on Tuesdays and Fridays.
Task set on Friday has deadline on Tuesday  4 Working Days
Task set on Tuesday has deadline on Friday  3 Working Days

## Slide 4: Planned Iterations
Iteration | Task | Start Date | End Date
1 | Login, Add bid, Bootstrap Functionality | Monday of Week 5 | Sunday of Week 6 (end)
2 | Drop bid, Slides for PM review, Web service, Update bid | Monday of Week 7 | Sunday of Week 8
3 | Rounds, Drop section, Dumping | Monday of Week 9 | Sunday of Week 10
4 | Deploying to AWS, UAT, Check UAT results, testing, debugging, redeploy | Monday of Week 11 | Sunday of Week 12
5 | Prepare Final presentation slides | Monday of Week 13 | Sunday of Week 14

## Slide 5: Roles & Task Allocation
Tricia Tan
Login framework & Add Bid functionality & bootstrap debugging
Loh Xiao Binn
Administrative, bootstrap functionality , test cases
d
Bao Xian
PM, Coding Advisor, Bootstrap validation & Login & Add Bid functionality
Yan Ning
Administrative, bootstrap framework , test cases
Casper Lim
Coding Advisor, Bootstrap validation & Login & Add Bid functionality

## Slide 6: Milestones
27 September – End of Iteration 1 programming
29 September – Prepare for PM review
3 October – PM review

## Slide 7: Buffer Time
Deadlines set at next meeting
Taking over/ Helping each other at meetings if any of us face any difficulties
Use Meeting time as buffer to debug

## Slide 8: Critical Path (Iteration 1)
Read Wiki
Schedule Iteration 1 tasks
Plan other Iterations
Create Login Page with Welcome Message
Create project database
Test
Login Page
Create addBid page
Create Bootstrap interface
Add .csv values into database
File validations
Test
Bootstrap
Test
Iteration 1
Start
End

## Slide 9: Bug Metrics
Wiki Question | Answer
What is the current value for the metric? | 
Did you have to take any action according to your mitigation plan? | Yes, debugging session was carried out during group meetings

## Slide 10: Roles & Responsibilities
Tricia Tan
Login framework & Add Bid functionality & bootstrap debugging
Loh Xiao Binn
Administrative, bootstrap functionality , test cases
d
Bao Xian
PM, Coding Advisor, Bootstrap validation & Login & Add Bid functionality
Yan Ning
Administrative, bootstrap framework , test cases
Casper Lim
Coding Advisor, Bootstrap validation & Login & Add Bid functionality

## Slide 11: PM in-charge of Milestone
Milestone | PM
Ref to slide 6 | Ref to slide 10

## Slide 12: Paired Programming Rotation Plan
Functionality | Paired Programmer | Paired Programmer
Login Framework | Tricia Tan | Casper Lim
Login Functionality & Validations | Casper Lim | Bao Xian
Add Bid | Bao Xian | Tricia Tan
Bootstrap Framework (1) | Bao Xian | Yan Ning
Bootstrap Framework (2) | Yan Ning | Xiao Binn
Bootstrap Validations & Debugging (1) | Xiao Binn | Casper Lim
Bootstrap Validations & Debugging (2) | Casper Lim | Yan Ning
Bootstrap Validations & Debugging (3) | Yan Ning | Bao Xian
Bootstrap Validations & Debugging (4) | Bao Xian | Tricia Tan