## Week 4
Person | Question | Week: 13/9/2019 to 19/9/2019
|  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
Tsang Bao Xian | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Read up on bootstrap and completed labs | Not a working day | Conducted pair programming with Tricia to begin add bid functionality and created required DAOs and class files | Met to check login functionality and add bid functionality, cleared doubts about project | Not a working day
| What will you do today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Familiarise with bootstrap functionality | Not a working day | Start on Add bid interface | Explain add bid functionalities, meet and test login page | Not a working day | Learn about bug metrics and class content, complete add bid functionality with Tricia
| Do you have any obstacles? | No | No | No | No | No | No | No
Loh Xiao Binn | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Not a working day | Not a working day | Met to check login functionality and add bid functionality, cleared doubts about project | Not a working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Not a working day | Not a working day | Meet with team to test login page functionalities and add bid | Not a working day | Learn about bug metrics and other contents in class
| Do you have any obstacles? | No | No | No | No | No | No | No
Casper Lim | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Created SQL tables and DAO for user to be used for login page. Also created common.php to be included in other pages | Uploaded CSV files to repository | Met to check login functionality and add bid functionality, cleared doubts about project. Pair programming with Tricia to complete login functionality | Not a working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Create database structure and authentication for login page | Not a working day | Meet to show login page functionalities and test together with group | Not a working day | Learn about bug metrics and other contents in class
| Do you have any obstacles? | No | No | No | No | No | No | No
Tricia Tan | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Not a working day | Coded html form and welcome message, pair programming with Bao Xian to create add bid functionality and required DAOs and class files | Met to check login functionality and add bid functionality, cleared doubts about project. Pair programming with Tricia to complete login functionality | Not a working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Begin html login form and welcome message upon successful login | Begin html login form and welcome message upon successful login | Meet to show login page functionalities and test together with group | Not a working day | Learn about bug metrics and class content, complete add bid functionality with Bao Xian
| Do you have any obstacles? | No | No | No | Personal commitments delayed task | Unable to test html form on working directory so not able to push onto central repository | No | No
Ong Yan Ning | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Not a working day | Clarified understanding of metrics, briefed team about changes to wiki | Met to check login functionality and add bid functionality, cleared doubts about project | Not a working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Not a working day | Read up on metrics and prepare to brief team on metrics requirements | Meet with team to test login page functionalities and add bid | Not a working day | Learn about bug metrics and other contents in class
| Do you have any obstacles? | No | No | No | Unclear of general project requirements | No | No | No