## Week 4
Person | Question | Week 4: 13 September to 15 September |  |  | Week 5: 16 September to 22 September | [6 empty] | Week 6: 23 September to 29 September | [6 empty] | Week 7: 30 September to 6 October | [6 empty] | Week 8: 7 October to 13 October | [6 empty] | Week 9: 14 October to 20 October | [6 empty] | Week 10: 21 October to 27 October | [6 empty] | Week 11: 28 October to 3 November | [6 empty] | Week 12: 4 November to 10 November
|  | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tsang Bao Xian | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Read up on bootstrap and completed labs | Not a working day | Conducted pair programming with Tricia to begin add bid functionality and created required DAOs and class files | Met to check login functionality and add bid functionality, cleared doubts about project | Not a working day | Learnt about bug metrics, partially completed add bid functionality with ability to view sections available per course | Met to discuss overall project structure and progress | Not a working day | Not a working day | Added cart and created bid class | Met to discuss bootstrap and coded bidding functionality | Not a working day | Discussed and fixed bootstrap bug | Added bootstrap validation with team | Minor bug fixes | Met to plan iter 2 and debugged some code | Not a working day | Meet to discuss slides and prepare for PM review | Deploy to AWS | Fixed deployment issues on AWS and PM review with team | Not a working day | Not a working day | Read up on JSON web service | Not working day | pair programming with Casper to do web service authenticate | pair programming with casper to complete web service add bid and prepare json checker | Meeting with team about json web service and json checker | Debugging with casper | Not working day | Dump user and debugging | Not a working day | Debugging, delete and update web service | Group meeting, PM review preparation and testing/debugging session | Application Demo and Progress Update | Not a working day | Non Working Day | pair programming with casper to dump bid and start/stop round | Pair programming with casper for drop section UI and web service, pair programming with tricia to connect update bid to database | non working day | non working day | meeting to update progress, pair programming with casper to protect json pages | non working day | non working day | Not a working day | Pair programming with Casper to fix update bid | meet to test and debug | JSON Test cases, debugging | Debugging and UAT | Non working day | Non working day | Non working day | Non working day
| What will you do today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Familiarise with bootstrap functionality | Not a working day | Start on Add bid interface | Explain add bid functionalities, meet and test login page | Not a working day | Learn about bug metrics and class content, complete add bid functionality with Tricia | Not a working day | Not a working day | Not a working day | Complete add bid functionality by creating bid objects upon submission | Meet to test bootstrap functionality and complete add bid | Complete bidding functionality with validations | Complete bidding functionality with validations | Meet to test bootstrap and add bid | Not a working day | Meet with team to test iteration 1 and schedule iteration 2 | Not a working day | Meet to discuss slides and prepare for PM review | Include milestones on presentations slides | Fix deployment issues and PM review with team | Not a working day | Not a working day | Read up on json and understand it | Not a working day | Pair programming with bao xian to create json web service for authentication | pair programming with Casper to complete web service add bid and prepare json checker | Meeting with team about json web service and json checker | Debugging with casper | Not working day | Debugging and doing dump table with casper | Not a working day | meeting for debugging and CP re-evaluation with team | meeting for debugging, testing, aws deployment and slides | Re deploy to AWS, Application Demo and Progress Update | Not a working day | Complete dump section and dump course with Casper | Pair programming with Casper to dump bid and dumb section | pair programming with casper for dump section | non working day | start on test cases (manual) | meeting to update progress, pair programming with casper to complete round 2 | non working day | non working day | non working day | Pair programming with Casper to fix update bid | meet to test and debug | Deploy to AWS | User Acceptance Test | Non working day | Non working day | Non working day | Non working day | Meet to reflect and debugging after UAT (Iter 3), plan for Iter 4
| Do you have any obstacles? | No | No | No | No | No | No | No | No | No | No | No | No | No | No time to programme, rescheduled to today | No | No | No | No | No | No | Deploying to AWS | No | No | No | No | No | No | No | No | No | No | Dump table requires round logic to complete so it's put on hold | No | No | No | No | No | No | no | no | no | no | no | no | no | No | no | no | no | no | no | no | no | no
Loh Xiao Binn | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Not a working day | Not a working day | Met to check login functionality and add bid functionality, cleared doubts about project | Not a working day | Learnt about scheduling and bug metrics | Met to discuss overall project structure and progress | Reinstalled wamp and tested out existing web pages | Pair programming with Yan Ning for bootstrap | Tried to fix bootstrap errors | Fixed bootstrap errors | Completed bootstrap functionality | Discussed and fixed bootstrap bug | Added bootstrap validation with team and tested login and bootstrap | Not a working day | spm pm rev slides | Not a working day | Meet to discuss iterations and prep for PM review | Pair programming with Casper for delete . Minor slides editing. | PM review with the team | Not a working day | Not a working day | Not a working day | Not working day | Not working day | Not working day | Meeting with team about json web service and json checker | Not working day | Not working day | Pair programming with Tricia | Continue with round clearing code | testing, slides | Group meeting, PM review preparation and testing/debugging session | Application Demo and Progress Update | Not a working day | Not a working day | Non Working Day | add protect.php and protect-admin.php to protect pages, with yan ning | non working day | non working day | neeting to update progress, project checklist for UAT | non working day | non working day | Not a working day | non working day | meet to test and debug, testing (manual) | testing (manual), debugging | Debugging and UAT | Non working day | Non working day | Non working day | Non working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Not a working day | Not a working day | Meet with team to test login page functionalities and add bid | Not a working day | Learn about bug metrics and other contents in class | Fix wamp issues with alias and read about bootstrap functionality to prepare to start programming | Reinstall wamp and try accessing php pages and create alias for project | Pair programming with yan ning for Bootstrap functionality | Fix errors for bootstrap code | Meet to discuss bootstrap | Complete bootstrap functionality | Not a working day | Meet to test bootstrap and add bid | Not a working day | Meet with team to test iteration 1 and schedule iteration 2 | non working day | Slides & bootstrap testing | Prep for Pm review | PM review with team | Not a working day | Not a working day | Not a working day | Not a working day | Not working day | Not working day | Meeting with team about json web service and json checker | read up on clearing logic | Not working day | Pair programming with Tricia 3-5 pm | Continue with round clearing code | meeting for debugging and CP re-evaluation with team | meeting for debugging, testing, aws deployment and slides | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day | Debugging Session with team | non working day | non working day | meeting to update progress and start on test cases | non working day | non working day | non working day | Not a working day | meet to test and debug | testing (manual) | testing (manual) | Non working day | Non working day | Non working day | Non working day | Meet to reflect and debugging after UAT (Iter 3), plan for Iter 4
| Do you have any obstacles? | No | No | No | No | No | No | No | No | No | No | Could not log in hence cannot test bootstrap on working directory | Cannot debug bootstrap errors so cannot commit | No | No | No | No | No | No | Waiting for iter1 critical path / whole project de???? | No | No | No | No | No | No | No | No | No | understanding round clearing logic | No | No | 2nd round logic | deduction of edollar function | No | No | No | No | No | No | no | no | no | no | no | no | No | no | no | no | no | no | no | no | no
Casper Lim | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Created SQL tables and DAO for user to be used for login page. Also created common.php to be included in other pages | Uploaded CSV files to repository | Met to check login functionality and add bid functionality, cleared doubts about project. Pair programming with Tricia to complete login functionality | Not a working day | Learnt about token and how to use web service | Met to discuss overall project structure and progress | Not a working day | Not a working day | Not a working day | Helped to debug and fix bootstrap errors | Rezip the sample data to the correct format. Troubleshoot and complete bootstrap.php. Create missing objects and DAO. Correct errors in add and remove dao. | Discussed and fixed bootstrap bug | Added bootstrap validation with team and tested login and bootstrap | Not a working day | Met to plan iter 2 and code some logic validation | Updated validation for edollar and amount if statement. | Validations for bootstrap. Test and debugged validations. | Pair programming with celine for delete. | PM review with the team | Pair programming with Tricia for add bid validations | Not a working day | Not a working day | Not working day | pair programming with Bao Xian to do web service authenticate | pair programming with Bao Xian to complete web service add bid and prepare json checker | Meeting with team about json web service and json checker | Debugging with Bao Xian | Not working day | Dump user and debugging | Not a working day | Debugging, delete and update web service | Group meeting, PM review preparation and testing/debugging session | Application Demo and Progress Update | Not a working day | Non Working Day | pair programming with baoxian to dump bid and start/stop round | Pair programming with bao xian for drop section UI and web service, | non working day | round 2 clearing logic | meeting to update progress, pair programming with bao xian to protect json pages | non working day | non working day | Not a working day | Pair programming with baoxian to fix update bid | meet to test and debug | JSON Test cases, debugging | Debugging and UAT | Non working day | Non working day | Non working day | Non working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Create database structure and authentication for login page | Not a working day | Meet to show login page functionalities and test together with group | Not a working day | Learn about bug metrics and other contents in class | Not a working day | Not a working day | Not a working day | Not a working day | Meet to test bootstrap functionality and help Celine and Yan ning with bootstrap errors | Not a working day | Not a working day | Meet to test bootstrap and add bid | Not a working day | Meet with team to test iteration 1 and schedule iteration 2 | Not a working day | Meet to discuss slides and prepare for PM review. Do the remaining logic validation. | Code delete.php, deleteDAO and delete processing | PM review with team | Pair programming with Tricia for add bid validations | Not a working day | Not a working day | Not a working day | Pair programming with bao xian to create json web service for authentication | pair programming with Bao Xian to complete web service add bid and prepare json checker | Meeting with team about json web service and json checker | Debugging with Bao Xian | Not working day | Debugging and doing dump table with bao xian | Not a working day | meeting for debugging and CP re-evaluation with team | meeting for debugging, testing, aws deployment and slides | Application Demo and Progress Update | Not a working day | Complete dump section and dump course with Bao Xian | Pair programming with Bao Xian to dump bid and dumb section | pair programming with baoxian for dump section | non working day | round 2 clearing logic (pair programming with tricia) | pair programming with bao xian to complete round 2 | non working day | non working day | non working day | Pair programming with baoxian to fix update bid | meet to test and debug | JSON test cases | User Acceptance Test | Non working day | Non working day | Non working day | Non working day | Meet to reflect and debugging after UAT (Iter 3), plan for Iter 4
| Do you have any obstacles? | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Dump table requires round logic to complete so it's put on hold | No | No | No | No | No | No | no | no | no | no | no | no | no | No | no | no | no | no | no | no | no | no
Tricia Tan | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Not a working day | Coded html form and welcome message, pair programming with Bao Xian to create add bid functionality and required DAOs and class files | Met to check login functionality and add bid functionality, cleared doubts about project. Pair programming with Tricia to complete login functionality | Not a working day | Learnt about bug metrics, partially completed add bid functionality with ability to view sections available per course | Met to discuss overall project structure and progress | Not a working day | Not a working day | Added cart and created bid class | Discussed bootstrap with group and coded bid functionality | Not a working day | Discussed and fixed bootstrap bug | Added bootstrap validation with team and tested login and bootstrap | Not a working day | Met to plan iter 2 and code some logic validation | Not a working day | Validations for bootstrap. Test and debugged validations. | Revise PM Review presentation slides | PM Review with team, Scheduling | Pair programming with Casper for add bid validations | Not a working day | Work on how to do the update bid function | Pair programming with Yan Ning for updateBid function | Not working day | Not working day | Meeting with team about json web service and json checker | Understand round clearing logic | Not working day | Sharing rounds logic with Celine/ Pair Programming | Continue with round logic | meeting for debugging and CP re-evaluation with team | Group meeting, PM review preparation and testing/debugging session | Application Demo and Progress Update | Include update bid function for database | Not a working day | Non Working Day | pair programming with baoxian to connect to database | non working day | round 2 clearing logic - settle update section size | meeting to update progress, | non working day | non working day | Not a working day | tried to do test cases | meet to test and debug | JSON Test cases, debugging | Debugging and UAT | Non working day | Non working day | Non working day | Non working day
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Begin html login form and welcome message upon successful login | Begin html login form and welcome message upon successful login | Meet to show login page functionalities and test together with group | Not a working day | Learn about bug metrics and class content, complete add bid functionality with Bao Xian | Not a working day | Not a working day | Not a working day | Complete add bid functionality by creating bid objects upon submission | Meet to test bootstrap functionality and complete add bid | Complete bidding functionality with validations | Complete bidding functionality with validations | Meet to test bootstrap and add bid | Not a working day | Meet with team to test iteration 1 and schedule iteration 2 | Not a working day | Remaining validations and group meeting | Revise PM Review presentation slides | PM review with team | Pair programming with Casper for add bid validations | Not a working day | Work on how to do the update bid function | Pair programming with Yan Ning for updateBid function | Not working day | Not working day | Meeting with team about JSON web service, JSON checker and update bid | Understand round clearing logic | Not working day | Sharing rounds logic with Celine/ Pari Programming | Continue with round logic | meeting for debugging and CP re-evaluation with team | meeting for debugging, testing, aws deployment and presentation slides | Application Demo and Progress Update | Include update bid function for database | Not a working day | Not a working day | Debugging Session with team | non working day | round 2 clearing logic (pair programming with Casper) | meeting to update progress | non working day | non working day | non working day | Try to do test cases | meet to test and debug | JSON test cases | User Acceptance Test | Non working day | Non working day | Non working day | Non working day | Meet to reflect and debugging after UAT (Iter 3), plan for Iter 4
| Do you have any obstacles? | No | No | No | Personal commitments delayed task | Unable to test html form on working directory so not able to push onto central repository | No | No | No | No | No | No | No | No | Rescheduled yesterday's task | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Difficulties in understanding round clearing logic | No | Understanding rounds logic | Encounter errors when filtering for each courses | Encounter errors when filtering for each courses | No | No | No | No | No | no | no | no | no | no | no | no | Test cases | no | no | No | no | no | no | no | no
Ong Yan Ning | What did you do yesterday? | Not a working day | Confirmed project schedule and iteration 1 tasks | Not a working day | Not a working day | Clarified understanding of metrics, briefed team about changes to wiki | Met to check login functionality and add bid functionality, cleared doubts about project | Not a working day | Clarified doubts about bootstrap, assisted group to upload previous schedule into google drive | Met to discuss overall project structure and progress | Practiced and understood bootstrap on labs | Pair programming with Celine for bootstrap functionalty | Tried to fix bootstrap errors | Fixed bootstrap errors | Completed bootstrap functionality | Discussed and fixed bootstrap bug | Added bootstrap validation with team and tested login and bootstrap | Created testcases | Bootstrap test cases | Tested and completed bootstrap function for student, course and section. | Meet to discuss slides and prepare for PM review | Bug metrics | PM review with the team | Not a working day | Not a working day | Not a working day | Pair programming with Tricia for update bid | Fix errors when new bidding amount is blank upon clicking | Not working day | Meeting with team about json web service and json checker | Add bid test cases | Test cases for update bid, delete bid and bootstrap part 1 (manual) | Bootstrap testcases (manual), Authenticate and bootstrap test cases (JSON) | Not a working day | Testing - login and add bid function (manual). Bugs logged in bug metrics. | Group meeting, PM review preparation and testing/debugging session | Application Demo and Progress Update | Not a working day | Not a working day | Non Working Day | add protect.php and protect-admin.php to protect pages, with xiao binn | non working day | test cases (manual) | meeting to update progress | non working day | non working day | Test cases (manual) | test cases (manual) | meet to test and debug | non working day | Non working day | Non working day | Non working day | Non working day | Json test cases
| What will you work on today? | Discuss and confirm project schedule, decide on iteration tasks and schedule iteration 1 | Not a working day | Not a working day | Read up on metrics and prepare to brief team on metrics requirements | Meet with team to test login page functionalities and add bid | Not a working day | Learn about bug metrics and other contents in class | Read up about bootstrap functionality | Practice bootstrap before pair programming | Pair programming with Celine for Bootstrap functionality | Fix errors for bootstrap code | Meet to discuss bootstrap | Complete bootstrap functionality | Not a working day | Meet to test bootstrap and add bid | Not a working day | Meet with team to test iteration 1 and schedule iteration 2 | Bootstrap testing and bug metric | Meet to discuss slides and prepare for PM review | Bug metrics | PM review with team | Not a working day | Not a working day | Not a working day | Pair programming with Tricia for update bid | Fix errors when new bidding amount is blank upon clicking | Not working day | Meeting with team about json web service and json checker | Add bid test cases | Test cases for update bid, delete bid and bootstrap part 1 (manual) | Test cases for all functions (json) | Update bid and delete bid test cases (JSON) | meeting for debugging and CP re-evaluation with team | Meeting for debugging, testing, aws deployment and slides | Application Demo and Progress Update | Not a working day | Not a working day | Not a working day | Debugging Session with team | non working day | start on test cases (manual) | meeting to update progress, test cases(manual) | non working day | non working day | testcases | Test cases (manual) | meet to test and debug | testing (manual) | User Acceptance Test | Non working day | Non working day | Non working day | Json test cases | Meet to reflect and debugging after UAT (Iter 3), plan for Iter 4
| Do you have any obstacles? | No | No | No | Unclear of general project requirements | No | No | No | Unsure about what bootstrap is for | No | No | Could not log in hence cannot test bootstrap on working directory | Cannot debug bootstrap errors so cannot commit | Had trouble understanding workings of bootstrap | No | No | No | No | No | Test cases - unsure whether am I doing it correctly. | No | No | No | No | No | No | No | No | No | No | No | No | Unsure whether the expected results is correct anot | No | No | No | No | No | No | no | no | no | no | no | no | no | No | no | no | no | no | no | no | no | no