## Schedule
Iteration No | Task No | Description | Planned Start Date / Time | Planned End Date / Time | Hours Planned | Actual Start Date / Time | Actual End Date / Time | Actual Hours Spent | Location | Status | Done By (Use Initials. Leader in bold)
1 | 1 | Read Project Wiki as a Team, Schedule tasks for iteration 1, Plan subsequent iterations | 2019-09-13 13:00 | 2019-09-13 15:00 | 2 | 2019-09-13 13:00 | 2019-09-13 14:00 | 1 | SIS Project Way | Completed | BX, XB, TT, CL
1 | 2 | Create Login Page with Welcome Message | 2019-09-14 10:00 | 2019-09-15 09:00 | 23 | [5 empty] | CL, TT
1 | 3 | Create users database and complete authentication for login | 2019-09-15 13:00 | 2019-09-17 10:00 | 45
1 | 4 | Meet and test login functionality | 2019-09-17 15:00 | 2019-09-17 16:00 | 1
1 | 6 | Create add bid functionality | 2019-09-15 10:00 | 2019-09-19 23:59 | 110
1 | 7 | Learn about metrics and brainstorm for metrics | 2019-09-19 12:00 | 2019-09-19 15:00 | 3
1 | 8 | Meet to confirm metrics and test add bid functionality | 2019-09-20 13:00 | 2019-09-20 15:00 | 2