## Slide 1: SPM Online Review
G4T4
PM: Tsang Bao Xian
Casper Lim Zhi Xin
Tricia Tan Li Lin
Ong Yan Ning
Loh Xiao Binn

## Slide 2
Project Manager: Tricia Tan
PM: Tsang Bao Xian
Casper Lim Zhi Xin
Tricia Tan Li Lin
Ong Yan Ning
Loh Xiao Binn
Application Demo
&
Progress Update
IS212 Software Project Management

## Slide 3: Functionalities
Wiki Question | Answer
Do you plan to drop/add any functionalities? | No
Do you plan to use any PHP frameworks? | No
Did you manage to finish login + 1 functionality? | Yes
What functionalities have you finished? | Login, add bid, bootstrap, [NEW] update bid, delete bid, JSON web service (partial), round 1 clearing logic (partial)
What is the IP address & admin password for your cloud deployment? | IP Address: 54.169.210.219 Admin password: @dm1in5PM

## Slide 4: Schedule Overview
Weekly Meetings on Tuesdays and Fridays.
Task set on Friday has deadline on Tuesday  4 Working Days
Task set on Tuesday has deadline on Friday  3 Working Days

## Slide 5: Planned Iterations status: On schedule
Iteration | Task | Start Date | End Date
1 | Login, Add bid, Bootstrap Functionality | Monday of Week 5 | Sunday of Week 6
2 | Drop bid, Slides for PM review, Web service, Update bid | Monday of Week 7 | Thursday of Week 9
3 | Rounds, Drop section, Dumping | Friday of Week 9 | Thursday of Week 11
4 | Deploying to AWS, UAT, Check UAT results, testing, debugging, redeploy | Friday of Week 11 | Thursday of Week 13
5 | Prepare Final presentation slides | Friday of Week 13 | Sunday of Week 14

## Slide 6
Roles & Task Allocation
Tricia Tan
PM, Coder
Loh Xiao Binn
Coder
d
Bao Xian
Coder
Yan Ning
Coder
Casper Lim
Coder

## Slide 7: Milestones
27 September – End of Iteration
3 October – PM review
13 October – End of Iteration 2
17 October – Application Demo
27 October – End of Iteration 3
31 October – User Acceptance Test
10 November – End of Iteration 4
17 November – Final submission
21 November – Final Presentation

## Slide 8: PM in-charge of Milestones
Milestone | PM
End of Iteration 1 | Bao Xian
PM Review | Bao Xian
End of Iteration 2 | Tricia
Application Demo | Tricia
End of Iteration 3 | Celine
User Acceptance Test | Celine
End of Iteration 4 | Casper
Final Submission | Casper
Final Presentation | Yan Ning

## Slide 9: Buffer Time
Deadlines set at next meeting
Taking over/ Helping each other at meetings if any of us face any difficulties
Use Meeting time as buffer to debug

## Slide 10
Add bid validation
1
1
2
2
2
Update bid
3
4
5
5
3
Testing & Debugging
6
6
6
6
1
Round 1 logic
7
7
8
8
2
Testing & Debugging
9
9
9
9
1
JSON checker
3
3
3
3
1
Update bid (JSON)
4
5
5
6
2
Delete bid (JSON)
6
7
7
8
2
Authentication
4
4
4
4
1
Testing & Debugging
5
5
5
5
1
Bootstrap
6
6
8
8
3
Create dump table
4
7
4
7
1
Create dump (user)
5
8
5
8
1
Testing & Debugging
9
9
9
9
1
Integration
10
10
10
10
1
Testing & debugging
11
11
11
11
1
Deployment
12
12
12
12
1
PM review slides
11
13
12
13
2
Working prototype
13
13
13
13
1
App demo, update process
14
14
14
14
2
Iteration 2
End
1
3
3
1
1

## Slide 11: Critical Path (Iteration 1)
Read Wiki
Schedule Iteration 1 tasks
Plan other Iterations
Create Login Page with Welcome Message
Create project database & Complete authentication
Test
Login Page
Create addBid page
Create Bootstrap interface
Add .csv values into database
File validations
Test
Bootstrap
Test
Iteration 1
Start
End

## Slide 12
AWS Deployment
JSON Web Service
Update Bid
Iteration
Integration
Online Review
Preparation
(Milestone)
Start
End
Validations (addBid, Bootstrap)
Drop Bid
Iteration Testing
Iteration Deployment
Critical Path (Iteration 2)

## Slide 13
Rounds
Iteration Integration
Iteration Testing
UAT
Preparation
(Milestone)
Start
End
JSON Dumping
Drop Section
Iteration Deployment
Critical Path (Iteration 3)

## Slide 14
Integration
AWS Deployment
Final Submission
Preparation
(Milestone)
Start
End
Web Service Testing
Web Application
Testing
Critical Path (Iteration 4)

## Slide 15: Bug Metrics
Wiki Question | Answer
What is the current value for the metric? | ??
Did you have to take any action according to your mitigation plan? | Debugging sessions are arranged when iteration points > 10 Yes, debugging session was carried out during group meetings

## Slide 16: Iter2: Paired Programming Rotation Plan
Functionality | Paired Programmer | Paired Programmer
Update Bid | Tricia Tan | Yan Ning
Drop Bid | Casper Lim | Xiao Binn
JSON Web Service | Bao Xian | Casper Lim
Round Clearing Logic | Tricia Tan | Xiao Binn

## Slide 17: Thank You